## Sheet1
Week | Date | Milestones
1 | 2016-02-08 | • Project Manager: 1.Jake 2.Colton: Make sure people know what they’re doing. Come up with weekly sprint objectives. Have a rough timeline done. • Responsive web developer team: 1. Kimberly 2.Jared 3. Alex: start rough draft website, start looking at angular JS. • Central webserver/DB developers: 1.Alex 2.Jared 3.Kimberly: rough layout for DB and start reading • Android App Developers: 1.Colton 2.Jake: Get software ready, start reading.
2 | 2016-02-15 | Get server up and running, Basic App running on an android device.
3 | 2016-02-23 | Website pull and push from DB and app pull and push from DB.
4 | 2016-02-29
5 | 2016-03-07
6 | 2016-03-14
7 | 2016-03-21
8 | 2016-03-28
9 | 2016-04-04
10 | 2016-04-11
11 | 2016-04-18
12 | 2016-04-25 | Wrap up for final presentation